## Slide 1
25G Mentor-mentee
  Training plan (MAY/2017 – MAY/2019)
28/JUN/2017
Mentor : Phong Huynh (1349)
Mentee: Pham Thanh (2001)
Renesas Electronics Corporation
Renesas design vietnam co., ltd
STS2/TD3

## Slide 2: Agenda
Traning Target Page 03
Current Status and Target Page 05
Gap analysis and Solution Page 06
Training Plan Page 11

## Slide 3: Training Target
Target: Engineer for test up to level 2 by May 2019
Can do Code Generator project task which has a certain difficult degree without help from Seniors/Leaders

## Slide 4: Training Target
Role | Skill | Skill Target |  | Target
Engineer For Test (Main Role) | Test environment construction | Have knowledge of the development environment (compiler, debugger), target environment (OS, middleware, applications, etc.), conduct test and evaluations. |  | 3
 | Test item extraction | Extract test items from various specifications and design specifications. | Round up and integrate and extracted test items into test specifications. | 2
 | Text execution | Conduct test according to the test specifications. | Round up the results and make a report. | 3
 | Failure analysis | Locate the cause of any trouble and make analysis of its influences and other side effects. | Take countermeasures against similar problem. | 2
 | Development process | Know and can follow development process well. | Can do feedback by looking at result of work. | 2
 | Communication Ability | Can report/explain the issue to teammate or customer | Can report work status in team | 2
 | Management Ability | Can schedule work and follow the schedule strictly | Can manage problem for any technical issues | 2
Engineer For Coding (Sub Role) | Readability | Have knowledge of the techniques for improving the source code readability and perform coding. |  | 2

## Slide 5: Current status
Role | Skill | Current Status
Engineer For Test (Main Role) | Test environment construction | Can setup environment following guideline of mentor or documents.
 | Test item extraction | Can create test spec for simply module with the support from mentor.
 | Text execution | Can execute test items for simple modules.
 | Failure analysis | Can analyze and fix simple failure.
 | Development process | Can follow the development process with the support from mentor.
 | Communication | Can report/explain the issue but unclear.
 | Management | Can follow the schedule from advisor.
Engineer For Coding (Sub Role) | Readability | Can code but not easy to understand.

## Slide 6: Gap analysis and solution (1/3)
Skill | Gap | Action Item |  | Milestone
 |  | Mentee | Mentor | 
Test Environment Construction | Lack of experience in setting up software environment . Lack of knowledge in Renesas tool usage | Set up software testing environment following mentor’s guideline from easy to difficult. Self investigate in tool manual with mentor’s support. Note the output for reference. | Provide materials, instructions. Confirm mentee’s understanding, give feedback. | May 2019
Test Item Extraction | Lack of knowledge in understanding the CG project architecture. Lack of experience in create new test item and test specification. | Read design specifications carefully, note and confirm with mentor to make more understanding and experience. Investigate test procedure and test format from existing test items and test specifications to extract test item correctly. | Provide existing test specification, document and give specific instructions. Confirm mentee’s understanding and output, give feedback. | May 2019

## Slide 7: Gap analysis and solution (2/3)
Skill | Gap | Action Item |  | Milestone
 |  | Mentee | Mentor | 
Test Item Execution | Lack of experience in conducting test. | Analyze each test item for better gaining experience. Learn from previous test reports. | Provide materials, instructions. Confirm mentee’s understanding, give feedback. | Jun 2019
Failure Analysis | Lack of experience in using 5why. Lack of knowledge to make a good countermeasure. | Learn from previous issue analysis. Propose or revise solution and make issue report for any problem to supervisor. | Provide specific instructions in each issue case. Confirm mentee’s understanding and output, give feedback. | Jun 2019

## Slide 8: Gap analysis and solution (2/3)
Skill | Gap | Action Item |  | Milestone
 |  | Mentee | Mentor | 
Software Coding | Not familiar with processing flow in source code at current project. | Self investigate source code. Learn feedback result with mentor’s confirmation. | Give a detail explain for mentee about processing flow in source code and project structure. Confirm mentee’s understanding and output, give feedback. | Jun 2019
MCU architecture | Lack of knowledge in hardware, especially in MCU architecture. | Investigate MCU architecture of RZ/T1, RL78, RX and RH850 family and self summary document to confirm the knowledge. | Provide materials, give a guideline and share the knowledge to mentee. Confirm mentee’s understanding and output, give feedback. | Jun 2019

## Slide 9: Gap analysis and solution (3/3)
Skill | Gap | Action item |  | Milestone
 |  | Mentee | Mentor | 
Communication Ability | Lack of experience to make a clear report. | Analyze previous report. Investigate the issue. | Share knowledge of complicated issue. Advice mentee, give feedback. | Jun 2019
Management Ability | Lack of experience in making schedule. | Estimate self-making schedule Take note, watch and learn from mentor, senior engineer. | Share knowledge how to manage tasks efficiently. Advice mentee, give feedback. | Jun 2019
Development Process | Lack of experience in how to follow up the development process | Investigate how to apply and feedback development process | Give instruction and share the knowledge to mentee Confirm mentee’ s report and give feedback | Jun 2019

## Slide 10: Training plan
May 2017
May 2019
Jul 2018
Set up environment on e2studio,
CS+, AP4, IAR for testing.
Output:
Set up new environment for
simple module with little support or
without support.
Test environment construction
Create test specification on
simple/medium modules of RX,RL78
MCU (DOC, CRC, WDT, POE,
DMAC,R12DA,LVD)
Output:
Test Specification with little
support.
Create test specification on
difficult modules
(MTU,TPU, SCI, S12AD)
Output:
Create test spec with coverage
full of functionality of module
testing.
Test item extraction
1.5
1.5
2
3
Set up environment for different
tools, new device, new IDE.
Output:
Set up new environment for new
device without support

## Slide 11: Training plan
May 2017
May 2019
Jul 2018
Failure analysis
Test execution
Need mentor’s support to find out
root cause and
recurrence prevention for module
issue.
Analyze, find out root cause and
recurrence prevention for
simple/difficult failure
1.5
1.0
2
3
Execute test specification on
simple/medium modules
of RX,RL78 MCU (DOC, CRC,
WDT, POE, DMAC,R12DA,LVD)
Output:
Test result with little support.
Execute test specification on
difficult modules (MTU,TPU, SCI,
S12AD)
Output:
Execute test with ensuring about
the procedures, report clearly, easy understanding

## Slide 12: Training plan
May 2016
May 2018
Jul 2017
Can understand RX, RL78
MCU architecture
Support in calculating workload to Develop process
Follow the process requirement with
the support of Mentor
Make project documents for project when applying development process.
Follow the process requirement
without the support of Mentor
Can follow schedule assigned from
leader
Raise alarm with Mentor’s advice
Can keep schedule and raise alarm if
necessary
2
2
2
1.5
1.5
1.5
Can understand another Renesas
MCU architecture
MCU architecture
Development process
Management ability

## Slide 13: Training plan
May 2016
May 2018
Jul 2017
Can report problem to leader
Can report work status in team
2
1.5
Conduct a code review of
created code.
Communication ability
Software coding
Create problem report
easy to understand
with mentor’s support.
Have sufficient knowledge of Java/ C# and maintain CG based on bug report.
1.5
2

## Slide 14: Mentor-Mentee interaction
Mentor
Mentee
Provide document, provide input, assign task
Discussion, Review (Email, meeting, direct discussion)
Create/Update Output, Report
Provide output, make report, propose idea

## Slide 15: Commitment
May 2018
Commitment after 2 years:
Achieve the target level 2 for all skills (except Test environment construction and Test execution achieve level 3)
Can do assigned tasks (Verification/Failure analysis) of CG projects without support.
Can support other related projects (PV,FIT Configurator)
Can manage development process for project.

## Slide 16
www.renesas.com
Thank you for your attention